## GanttChart
INSERT YOUR TITLE HERE
| Project Start Date | 2022-03-21 |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42
| Project Leader | [5 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02
 | time axis 2022-03-21 to 2023-01-08
NO. | TASKS | ASSIGNED TO | START | END | DAYS | STATUS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Review of Related Literature/ Documents (Internet/Books/Magazines) | All | 2022-03-21 | 2022-03-27 | 7 | Done
2 | Document Review | All | 2022-03-28 | 2022-04-03 | 7 | Done
3 | Observation | All | 2022-04-04 | 2022-04-10 | 7 | Done
4 | Interview | All | 2022-04-11 | 2022-04-17 | 7 | Done
5 | Documentation | All | 2022-04-18 | 2022-04-24 | 7 | Done
6 | Identification of users | All | 2022-04-25 | 2022-04-27 | 3 | Done
7 | Identification of system requirements | All | 2022-04-28 | 2022-05-01 | 4 | Done
8 | Design context level diagram | All | 2022-05-02 | 2022-05-04 | 3 | Done
9 | Design data flow diagram | All | 2022-05-05 | 2022-05-08 | 4 | Done
10 | Design use case diagram | All | 2022-05-09 | 2022-05-15 | 7 | Done
11 | Design activity diagram | All | 2022-05-16 | 2022-05-22 | 7 | Done
12 | Design database | All | 2022-05-23 | 2022-05-29 | 7 | Done
13 | Design system architecture | All | 2022-05-30 | 2022-06-05 | 7 | Done
14 | Design the Graphical User Interface | All | 2022-06-06 | 2022-06-19 | 14 | Done
15 | Collecting Tool Datasets | Lim | 2022-06-20 | 2022-06-26 | 7 | On-Going
16 | Develop Image recognition scanner | Maalam | 2022-06-27 | 2022-07-03 | 7 | On-Going
17 | Develop Camera AI Scanner | Baculio | 2022-07-04 | 2022-07-10 | 7 | Not Yet Started
18 | Develop the Splash Screen |  | 2022-07-11 | 2022-07-17 | 7 | Not Yet Started
19 | Develop the Home Page |  | 2022-07-18 | 2022-07-24 | 7 | Not Yet Started
20 | Develop Database for Tool Catalogs |  | 2022-07-25 | 2022-07-31 | 7 | On-Going
21 | Develop Search Bar and Sorting System |  | 2022-08-01 | 2022-08-07 | 7 | Not Yet Started
22 | Develop Tool Scan or Upload Page |  | 2022-08-08 | 2022-08-14 | 7 | Not Yet Started
23 | Develop Post tool Recognition Pop-up |  | 2022-08-15 | 2022-08-21 | 7 | Not Yet Started
24 | Develop Tool Guides and Information Page |  | 2022-08-22 | 2022-08-28 | 7 | Not Yet Started
25 | Develop Favorites Page |  | 2022-08-29 | 2022-09-04 | 7 | Not Yet Started
26 | Develop Settings and Configurations Page |  | 2022-09-05 | 2022-09-11 | 7 | Not Yet Started
27 | Export and Building of APK |  | 2022-09-12 | 2022-09-18 | 7 | Not Yet Started
28 | Last Day of Development |  | 2022-09-18 | 2022-10-23 | 7
29 | Development of Test Plan | All | 2022-10-24 | 2022-10-26 | 3
30 | Unit Testing | All | 2022-10-27 | 2022-10-29 | 3
31 | Integration Testing | All | 2022-10-30 | 2022-11-01 | 3
32 | System Testing | All | 2022-11-02 | 2022-11-04 | 3
33 | Development of User Manual | All | 2022-11-05 | 2022-11-07 | 3
34 | User's Training | All | 2022-11-08 | 2022-11-10 | 3
35 | Functional Testing | All | 2022-11-11 | 2022-11-13 | 3
36 | Usability Testing | All | 2022-11-14 | 2022-11-16 | 3
37 | Chapter 1 Manuscript | All | 2022-05-30 | 2022-06-05 | 7
38 | Chapter 2 Manuscript | All | 2022-03-21 | 2022-03-27 | 7
39 | Chapter 3 Manuscript | All | 2022-03-21 | 2022-11-16 | 241
40 | Chapter 4 Manuscript | All | 2022-11-17 | 2022-11-23 | 7
41 | Chapter 5 Manuscript | All | 2022-11-24 | 2022-11-30 | 7
42 | Other Documents (e.g. Video Presentation, Poster) | All | 2022-12-01 | 2022-12-13 | 13